## WIP Schedule
WIP Schedule (cost-to-cost) | [14 empty] | As of: | YYYY-MM-DD
Yellow cells are inputs. Everything else calculates. Replace the sample rows with your jobs; see the Definitions tab.
Job # | Job name | Original contract | Approved change orders | Revised contract | Original estimated cost | Estimated cost at completion (EAC) | Cost to date | % complete (cost-to-cost) | Earned revenue | Billed to date | Over billing | Under billing | Estimated gross profit | GP % at completion | Gross profit earned to date | Cost to complete | Backlog (revenue remaining) | Pending change orders (exposure) | Risk label
1001 | Sample: Medical office building | 12500000 | 450000 |  | 11200000 | 11650000 | 7340000 |  |  | 8100000 | [7 empty] | 120000
1002 | Sample: K-12 school addition | 8200000 | 0 |  | 7380000 | 7520000 | 2250000 |  |  | 2050000 | [7 empty] | 0
1003 | Sample: Warehouse tilt-up | 21000000 | 1250000 |  | 19400000 | 20900000 | 15675000 |  |  | 16500000 | [7 empty] | 300000
1004 | Sample: Tenant improvement | 1850000 | -40000 |  | 1650000 | 1640000 | 1640000 |  |  | 1810000 | [7 empty] | 0
1005 | Sample: Parking structure | 15400000 | 0 |  | 14000000 | 0 | 0 |  |  | 0 | [7 empty] | 0
Totals
Net over/(under) billing

## Definitions
Term | Definition
Revised contract | Original contract + approved change orders. Pending change orders are shown separately as exposure, never added.
Estimated cost at completion (EAC) | Your current forecast of total job cost. The WIP schedule is only as good as this number: update it monthly.
% complete (cost-to-cost) | Cost to date ÷ EAC, capped at 100%. The most common method for construction revenue recognition (confirm your method with your CPA).
Earned revenue | Revised contract × % complete.
Over billing | Billed to date − earned revenue, when positive. A liability: you've billed ahead of the work.
Under billing | Earned revenue − billed to date, when positive. An asset, but sureties and lenders watch it closely.
Estimated gross profit | Revised contract − EAC. GP % at completion = estimated gross profit ÷ revised contract.
Fade / gain | Month-over-month change in GP % at completion. Track it by keeping each month's schedule (one file or tab per month).
Backlog | Revised contract − earned revenue: the revenue still to be earned on signed work.
Risk label | No forecast (EAC blank), At risk (GP % below 0), Watch (below 10%), otherwise On track. Adjust thresholds to your policy.
Common mistakes | Blank EACs treated as zero; summing running balances across months; pending COs added to contract; job lists that differ between PM and accounting systems.
Automating it | Pull contracts/EAC/cost from Procore and billing/job cost from accounting nightly, match jobs with a crosswalk, check data quality, snapshot each month-end. Guide: https://www.buildflows.ai/articles/construction-wip-reporting-power-bi

## Power BI measures
Measure | DAX (assumes a fact table 'WIP' with one row per job per month; adjust names)
Revised Contract | Revised Contract = SUM ( WIP[OriginalContract] ) + SUM ( WIP[ApprovedCOs] )
Pct Complete | Pct Complete = DIVIDE ( SUM ( WIP[CostToDate] ), SUM ( WIP[EAC] ) )
Earned Revenue | Earned Revenue = SUMX ( VALUES ( WIP[JobId] ), [Revised Contract] * MIN ( 1, [Pct Complete] ) )
Over Billing | Over Billing = SUMX ( VALUES ( WIP[JobId] ), MAX ( 0, CALCULATE ( SUM ( WIP[BilledToDate] ) ) - [Earned Revenue] ) )
Under Billing | Under Billing = SUMX ( VALUES ( WIP[JobId] ), MAX ( 0, [Earned Revenue] - CALCULATE ( SUM ( WIP[BilledToDate] ) ) ) )
GP % at Completion | GP % at Completion = DIVIDE ( [Revised Contract] - SUM ( WIP[EAC] ), [Revised Contract] )
Note | Compute per job, then sum (SUMX over jobs). Never sum percentages, and take balances from the latest month only.

## About
Free WIP schedule template from Build Flows (www.buildflows.ai). Use it, change it, share it.
Sample rows are fictional. Replace them with your jobs.
Want this computed nightly from Procore and your accounting system, with data-quality checks? https://www.buildflows.ai/offers/wip-cash-forecast
Questions: charley@buildflows.ai